## Year Plan
MY PROJECT PLAN FOR 2022
Quarter | Goals | Sub-Goals | Start | End | Status | Actual Start | Actual End | Note
Quarter 1 | Project requirements and initialization |  | 2022-01-01 | 2022-03-31 | DONE | 2022-01-01 | 2022-03-31
Project planing
Declare workflow
Write SRS for US-001 to US-012
Initialize source code
Setup environments & CI/CD pipeline
Member training
Deliver the 1st-beta version
Quarter 2 | Deliver US-001 to US-012 |  | 2022-04-01 | 2022-06-30 | IN PROGRESS | 2022-04-01 | 2022-06-30
Coding for US-001 to US-012
Tesing for US-001 to US-012
Deliver US-009 to US-0012
Write SRS for US-013 to US-024
Team retrospective
Quarter 3 | Deliver US-013 to US-024 |  | 2022-07-01 | 2022-09-30 | NOT STARTED | 2022-07-01 | 2022-09-30
Coding for US-013 to US-024
Tesing for US-013 to US-024
Deliver US-013 to US-024
Write SRS for US-025 to US-032
Team retrospective
Quarter 4 | Deliver US-025 to US-036 |  | 2022-10-01 | 2022-12-31 | NOT STARTED | 2022-10-01 | 2022-12-31
Coding for US-025 to US-036
Tesing for US-025 to US-036
Deliver US-025 to US-036
Write SRS for US-013 to US-024
Team retrospective
Project closing
Year-end party

## Quarter Plan
MY PROJECT WEEK PLAN Q1-Y22
Week | Goals | Deliverables |  | PIC | Status | Start | End | Actual Start | Actual End | Note
1 | Project planing and Declare workflow | Planing, workflow, SRS |  | Jane | DONE | 2022-01-03 | 2022-01-08
2 | Write SRS for US-001 to US-012 | User Stories, SRS, mockup, transfer |  | Jane | DONE | 2022-01-10 | 2022-01-21
3 | Initialize source code | Source code skeleton, database design |  | Thomas | DONE | 2022-01-17 | 2022-01-21
4 | Setup environments & CI/CD pipeline | Git repo, CICD pipeline, quality gate |  | HieuVV | DONE | 2022-01-31 | 2022-02-11
5 | Testing | Test cases, scripts, report |  | Bob | DONE | 2022-02-07 | 2022-02-18
6 | Deliver the 1st-beta version | The first beta version |  | Jane | DONE | 2022-02-21 | 2022-02-21
Week | Goals | Sub-Goals | Effort Time (h) | PIC | Status | Start | End | Actual Start | Actual End | Note
1 | Project planing and Declare workflow |  | 36 | Jane | DONE | 2022-01-03 | 2022-01-08
2 | Write SRS for US-001 to US-012 |  | 80 | Jane | DONE | 2022-01-10 | 2022-01-21
|  | Collect requirements | 16 | Jane | DONE | 2022-01-10 | 2022-01-11
|  | Declare User stories | 24 | Jane | DONE | 2022-01-12 | 2022-01-14
|  | Create mockups | 24 | Jane | DONE | 2022-01-17 | 2022-01-19
|  | SRS verification | 8 | Jane | DONE | 2022-01-20 | 2022-01-20
|  | Transfer requirements | 8 | Jane | DONE | 2022-01-21 | 2022-01-21
3 | Initialize source code |  | 72 | Thomas | IN PROGRESS | 2022-01-17 | 2022-01-21
|  | Define and build database | 24 | Thomas | DONE | 2022-01-17 | 2022-01-19
|  | Build C# back-end skeleton | 16 | Thomas | DONE | 2022-01-20 | 2022-01-21
|  | Build front-end code structure | 16 | Thomas | IN PROGRESS | 2022-01-22 | 2022-01-23
|  | Intergrate sample api | 16 | Thomas | NOT STARTED | 2022-01-24 | 2022-01-25
4 | Setup environments & CI/CD pipeline |  | 92 | HieuVV | IN PROGRESS | 2022-01-31 | 2022-02-11
|  | Setup Git repository for project | 12 | HieuVV | DONE | 2022-01-31 | 2022-02-02
|  | Setup cloud-based environments | 16 | HieuVV | DONE | 2022-02-03 | 2022-02-04
|  | Setup Infra-as-Code for project | 32 | HieuVV | DONE | 2022-02-05 | 2022-02-08
|  | Setup CI/CD pipeline | 16 | HieuVV | IN PROGRESS | 2022-02-09 | 2022-02-10
|  | Setup CI quality gate for pipeline | 16 | HieuVV | NOT STARTED | 2022-02-10 | 2022-02-11
5 | Testing |  | 60 | Bob | IN PROGRESS | 2022-02-07 | 2022-02-18
|  | Define test cases | 16 | Bob | DONE | 2022-02-07 | 2022-02-08
|  | Verify test cases | 8 | Bob | IN PROGRESS | 2022-02-09 | 2022-02-09
|  | Perform test | 16 | Bob | IN PROGRESS | 2022-02-10 | 2022-02-11
|  | Regression test | 20 | Bob | IN PROGRESS | 2022-02-14 | 2022-02-18
|  | Collect result and make test report | 20 | Bob | NOT STARTED | 2022-02-14 | 2022-02-18
6 | Deliver the 1st-beta version |  | 36 | Jane | BLOCKED | 2022-02-21 | 2022-02-21
Formulas:
End = [Start]+5

## Sheet1
Week | <component>
2020-10-01
2020-10-08
2020-10-15
2020-10-22
2020-10-29
2020-11-05
2020-11-12
2020-11-19
2020-11-26
2020-12-03
2020-12-10
2020-12-17
| Goals | Goals